## Task List
Unified Protein Structure Prediction Tool — Implementation Plan
MVP: ~5 weeks (Phase 1+2) ¦ Full BV-BRC: ~10 weeks ¦ Following APPSERVICE_IMPLEMENTATION_PLAN.md patterns
ID | Phase | Task | Description | Owner | Priority | Status | Depends On | Effort (h) | Week | Deliverable | Notes
PHASE 0: PROJECT SETUP & SCAFFOLDING (Week 1)
P0.1 | Phase 0 | Create PredictStructureApp directory | Scaffold directory following boltzApp pattern: app_specs/, service-scripts/, scripts/, lib/, container/, docs/, tests/, test_data/ | Dev | Critical | Not Started | - | 1 | W1 | PredictStructureApp/ | Mirror boltzApp structure exactly
P0.2 | Phase 0 | Create Makefile | Copy boltzApp/Makefile, update TOP_DIR, CURRENT_DIR. Standard targets: all, bin, deploy-client, deploy-service, deploy-specs | Dev | Critical | Not Started | - | 0.5 | W1 | Makefile | Identical pattern across all apps
P0.3 | Phase 0 | Create CLAUDE.md | Document unified app conventions, adapter pattern, parameter mapping, testing strategy | Dev | High | Not Started | - | 1 | W1 | CLAUDE.md
P0.4 | Phase 0 | Create pyproject.toml | Python package config for predict_structure/ with click, biopython, pandas deps | Dev | High | Not Started | - | 0.5 | W1 | pyproject.toml
P0.5 | Phase 0 | Check CEPI repo (github.com/wilke/CEPI) | Review CEPI for any reusable patterns, CLI designs, or shared infrastructure | Dev | Medium | Not Started | - | 1 | W1 | Notes | Repo appears private — get access
PHASE 1: PYTHON CLI + ADAPTERS (Weeks 1-4)
P1.1 | Phase 1 | Create base adapter class | Abstract class: prepare_input(), build_command(), run(), normalize_output(). Define unified param names. | Dev | Critical | Not Started | - | 3 | W1 | predict_structure/adapters/base.py
P1.2 | Phase 1 | Implement BoltzAdapter | FASTA→YAML conversion, --diffusion_samples→num_samples mapping, mmCIF→PDB output conversion, confidence JSON extraction | Dev | Critical | Not Started | P1.1 | 4 | W1-2 | predict_structure/adapters/boltz.py | Use boltz predict CLI directly
P1.3 | Phase 1 | Implement ESMFoldAdapter (HuggingFace) | Direct FASTA pass-through, --num-recycles mapping, PDB output (native), pLDDT extraction from B-factors | Dev | Critical | Not Started | P1.1 | 3 | W2 | predict_structure/adapters/esmfold.py | Use HF esm-fold-hf, not legacy
P1.4 | Phase 1 | Implement ChaiAdapter | FASTA pass-through, A3M→Parquet MSA conversion via a3m-to-pqt, mmCIF→PDB output, scores.npz parsing | Dev | High | Not Started | P1.1 | 4 | W2-3 | predict_structure/adapters/chai.py | Chai uses uv, not pip
P1.5 | Phase 1 | Implement AlphaFoldAdapter | FASTA pass-through, precomputed MSA dir structure, DB path pass-through, PDB output (native), ranking_debug.json parsing | Dev | High | Not Started | P1.1 | 4 | W3 | predict_structure/adapters/alphafold.py | Keep AF2 DB paths as pass-through
P1.6 | Phase 1 | Implement unified CLI entry point | click-based CLI: predict-structure <tool> <input.fasta> -o <dir> [--num-samples, --num-recycles, --seed, --device, --msa, --boltz-*, --chai-*, etc.] | Dev | Critical | Not Started | P1.2,P1.3 | 3 | W2 | predict_structure/cli.py
P1.7 | Phase 1 | Input format conversion module | FASTA→Boltz YAML (with optional MSA injection), A3M→Parquet for Chai, single-seq A3M generator for AF2 no-MSA mode | Dev | High | Not Started | P1.1 | 3 | W2-3 | predict_structure/converters.py | BioPython for PDB/CIF
P1.8 | Phase 1 | Output normalization module | mmCIF→PDB (gemmi/BioPython), confidence JSON schema: {plddt_mean, ptm, per_residue_plddt[]}, metadata.json with tool/params/runtime | Dev | High | Not Started | P1.1 | 3 | W3 | predict_structure/normalizers.py | All tools → same output dir layout
P1.9 | Phase 1 | Docker execution backend | subprocess.run() wrapping docker run commands, volume mounting for input/output/cache, GPU device passthrough | Dev | High | Not Started | P1.6 | 2 | W3 | predict_structure/backends/docker.py
P1.10 | Phase 1 | Unit tests for adapters | Test each adapter: param mapping, command building, output normalization. Use pilot target subset (1UBQ, 4LZT). | Dev | High | Not Started | P1.2-P1.5 | 4 | W3-4 | tests/test_adapters.py
P1.11 | Phase 1 | Integration test: end-to-end prediction | Run predict-structure boltz/esmfold on test FASTA, verify normalized output structure | Dev | High | Not Started | P1.9,P1.10 | 3 | W4 | tests/test_integration.py | Requires GPU for full test
P1.12 | Phase 1 | Create test_data/ | simple_protein.fasta (1UBQ), multimer.fasta, protein_ligand.yaml (Boltz), params.json (BV-BRC test), validate_output.sh | Dev | Medium | Not Started | - | 2 | W1 | test_data/ | Follow Stream C pattern from APPSERVICE plan
PHASE 2: ESMFOLD HUGGINGFACE MIGRATION (Weeks 3-5)
P2.1 | Phase 2 | Audit existing hf_fold.py | Review ESMFoldApp/esm_hf/scripts/hf_fold.py, identify gaps vs legacy esm-fold CLI, document parameter parity | Dev | Critical | Not Started | - | 2 | W3 | Notes
P2.2 | Phase 2 | Promote hf_fold.py to primary CLI | Add --num-recycles, --chunk-size, --fp16, --max-tokens-per-batch, --cpu-only flags. Entry point: esm-fold-hf | Dev | Critical | Not Started | P2.1 | 3 | W3-4 | scripts/esm-fold-hf
P2.3 | Phase 2 | Create lightweight Docker image | FROM nvidia/cuda → pip install transformers torch → COPY esm-fold-hf. Target: ~8GB (vs ~15GB legacy) | Dev | Critical | Not Started | P2.2 | 2 | W4 | container/Dockerfile.esmfold-hf | No OpenFold dependency
P2.4 | Phase 2 | Build BV-BRC runtime layer | FROM dxkb/esmfold-hf → add Perl 5.40 + CPAN + BV-BRC modules. Follow Dockerfile.boltz-bvbrc pattern exactly. | Dev | High | Not Started | P2.3 | 2 | W4 | container/Dockerfile.esmfold-hf-bvbrc | 3-layer Docker pattern
P2.5 | Phase 2 | Validate output parity on pilot targets | Run both legacy esm-fold and new esm-fold-hf on 10 pilot targets. Compare pLDDT, RMSD. Acceptance: <0.5Å RMSD delta. | Dev | Critical | Not Started | P2.3 | 4 | W4-5 | results/esmfold_parity/ | GPU required
P2.6 | Phase 2 | Update ProteinFoldingApp CWL | Change esmfold-predict.cwl baseCommand from esm-fold to esm-fold-hf, update Docker image reference | Dev | Medium | Not Started | P2.5 | 1 | W5 | cwl/tools/esmfold-predict.cwl
P2.7 | Phase 2 | Deprecation notice for legacy esm-fold | Add deprecation warning to ESMFoldApp, update README, document migration guide | Dev | Low | Not Started | P2.5 | 1 | W5 | docs/MIGRATION.md
PHASE 3: CWL INTEGRATION (Weeks 5-7)
P3.1 | Phase 3 | Create predict-structure.cwl tool definition | CWL v1.2 CommandLineTool wrapping unified CLI. Inputs: tool enum, FASTA, output_dir, all unified params. DockerRequirement. | Dev | High | Not Started | P1.11 | 3 | W5 | cwl/tools/predict-structure.cwl | Follow ProteinFoldingApp CWL pattern
P3.2 | Phase 3 | Create unified stability pipeline CWL | Workflow: predict-structure → stabilinnator. Follow protein_stability_pipeline.cwl pattern. Tool selector as input enum. | Dev | High | Not Started | P3.1 | 3 | W5-6 | cwl/workflows/unified_stability_pipeline.cwl | Chain like ProteinEngineeringWorkflows
P3.3 | Phase 3 | Add --backend cwl mode to CLI | predict-structure --backend cwl generates CWL job YAML and submits to GoWe. Reuse existing GoWe submission pattern. | Dev | Medium | Not Started | P3.1 | 3 | W6 | predict_structure/backends/cwl.py
P3.4 | Phase 3 | Update ProteinFoldingApp experiments | Optionally run experiments 1-4 through unified tool. Backwards-compatible with direct CWL tools. | Dev | Medium | Not Started | P3.1 | 2 | W6-7 | Updated experiment CWLs
P3.5 | Phase 3 | CWL validation tests | cwltool --validate on all new CWL files. End-to-end: cwltool predict-structure.cwl test_job.yml | Dev | High | Not Started | P3.1,P3.2 | 2 | W7 | tests/test_cwl.sh
PHASE 4: BV-BRC APPSERVICE INTEGRATION (Weeks 7-10)
P4.1 | Phase 4 | Create PredictStructure.json app_spec | Follow Boltz.json pattern exactly. Add "tool" enum param (boltz/chai/alphafold/esmfold/auto). Unified params + tool-specific pass-through sections. | Dev | Critical | Not Started | - | 3 | W7 | app_specs/PredictStructure.json | See Boltz.json for schema
P4.2 | Phase 4 | Create App-PredictStructure.pl | BV-BRC AppScript pattern: preflight() + run_predict_structure(). Dispatch to adapters. Download/upload workspace files. | Dev | Critical | Not Started | P4.1 | 6 | W7-8 | service-scripts/App-PredictStructure.pl | Follow App-Boltz.pl pattern
P4.3 | Phase 4 | Implement preflight() resource estimation | Dynamic: tool + samples + sequence length → CPU/memory/runtime/GPU. Follow Boltz heuristics: +1h/sample, +500MB/recycle. | Dev | High | Not Started | P4.2 | 2 | W8 | In App-PredictStructure.pl | ESMFold: no GPU policy needed
P4.4 | Phase 4 | Implement tool auto-routing logic | YAML input→Boltz, multi-chain FASTA→Chai, single protein+no MSA→ESMFold, single protein+MSA→AlphaFold | Dev | High | Not Started | P4.2 | 2 | W8 | In App-PredictStructure.pl | Open question: exact heuristic
P4.5 | Phase 4 | Implement workspace download/upload | download_workspace_file(), upload_results() with recursive file finding. File type detection: structure/json/fasta/binary. | Dev | High | Not Started | P4.2 | 2 | W8 | In App-PredictStructure.pl | Copy pattern from App-Boltz.pl
P4.6 | Phase 4 | Create Docker image for unified app | Multi-tool image OR delegation to per-tool images. Option A: fat image with all tools. Option B: delegate to existing containers. | Dev | High | Not Started | P4.2 | 4 | W8-9 | container/Dockerfile.PredictStructure-bvbrc | Delegation = smaller, more maintainable
P4.7 | Phase 4 | Create Apptainer/Singularity definition | Bootstrap: docker, From: dxkb/predict-structure-bvbrc:latest-gpu. Follow boltz-bvbrc.def pattern. | Dev | Medium | Not Started | P4.6 | 2 | W9 | container/predict-structure-bvbrc.def | For HPC/SLURM deployment
P4.8 | Phase 4 | BV-BRC integration tests | Test with params.json locally (no workspace). Test preflight for each tool. Test workspace mock. | Dev | High | Not Started | P4.2-P4.5 | 3 | W9 | tests/ | Follow Stream C from APPSERVICE plan
P4.9 | Phase 4 | GPU validation on HPC | Deploy Apptainer image to gpu2 partition. Run each tool through App-PredictStructure.pl. Validate SLURM resource allocation. | Dev | Critical | Not Started | P4.7,P4.8 | 4 | W9-10 | Test results | Needs A100¦H100¦H200
P4.10 | Phase 4 | Documentation and examples | User guide, parameter reference, example params.json for each tool, troubleshooting guide | Dev | Medium | Not Started | P4.9 | 3 | W10 | docs/
P4.11 | Phase 4 | Deploy to BV-BRC production | make deploy-service → $(TARGET)/services/app_service/app_specs/. Register app. Verify in web UI. | Dev | Critical | Not Started | P4.9,P4.10 | 2 | W10 | Deployed app | Coordinate with BV-BRC ops
PHASE 5: ENHANCEMENTS (Post-MVP)
P5.1 | Phase 5 | Ensemble mode | predict-structure --ensemble runs all tools, picks best by pTM/pLDDT. Uses ProteinFoldingApp comparison infra. | Dev | Medium | Not Started | P4.11 | 8 | W11+ | predict_structure/ensemble.py | Open question
P5.2 | Phase 5 | stabiliNNator integration | predict-structure --analyze-stability chains prediction→stability analysis. Reuse protein_stability_pipeline.cwl pattern. | Dev | Medium | Not Started | P4.11 | 4 | W11+ | CLI flag + CWL step
P5.3 | Phase 5 | Non-protein entity support | Ligands/DNA/RNA: only Boltz supports natively via YAML. Unified CLI passes Boltz YAML through; warns for other tools. | Dev | Low | Not Started | P4.11 | 6 | W12+ | Extended adapters | Scope creep risk
P5.4 | Phase 5 | Version pinning and registry | Track tool versions per Docker image. --tool-version flag. Version compatibility matrix. | Dev | Low | Not Started | P4.11 | 4 | W12+ | predict_structure/versions.py
SUMMARY
Total Tasks: | 49
Total Effort (h): | 125
Not Started: | 44
In Progress: | 0
Done: | 0

## Risk Register
Risk Register — Unified Protein Structure Prediction Tool
ID | Risk | Likelihood | Impact | Score | Mitigation | Owner | Status | Contingency
R1 | Upstream API Breaking Changes | High | High | 9 | Pin tool versions in Docker images; adapter layer absorbs CLI changes; semantic versioning for unified tool | Dev | Open | Roll back to last known-good Docker tag
R2 | Chai MSA Format Conversion | Medium | Medium | 3 | A3M→Parquet conversion in adapter with size validation; test with MSAs from 8 to 50K sequences | Dev | Open | Fall back to Chai --use-msa-server
R3 | GPU Memory Fragmentation | Medium | High | 6 | Per-tool VRAM profiles in preflight(); auto-select batch size; --device auto based on nvidia-smi | Dev | Open | Fall back to CPU for ESMFold; queue retry for others
R4 | ESMFold HF Model Parity | Low | High | 6 | Validate on 10 pilot targets before deprecating legacy; acceptance: <0.5Å RMSD delta | Dev | Open | Keep legacy Docker image as fallback
R5 | AlphaFold2 DB Infrastructure | Medium | Medium | 3 | Keep AF2 database paths as pass-through in adapter; don't abstract DB config | Dev | Open | Document manual DB setup steps
R6 | Scope Creep (ligands, DNA/RNA) | High | Medium | 6 | MVP is protein-only FASTA; Boltz YAML pass-through for advanced entities; Phase 5 for full support | Dev | Open | Defer to Phase 5; use Boltz directly for non-protein
R7 | CEPI Integration Uncertainty | Medium | Low | 3 | Repo is private/inaccessible. Once access granted, evaluate for shared patterns. Don't block MVP. | Dev | Open | Proceed without CEPI; retrofit if valuable
R8 | Multi-tool Docker Image Size | Medium | Medium | 3 | Use delegation pattern (App-PredictStructure calls per-tool containers) instead of fat image | Dev | Open | Ship per-tool images; unified app delegates

## BV-BRC Patterns
BV-BRC AppService Patterns Reference
Pattern | Description | Example (Boltz) | File Location | Required for Unified App | Notes
app_specs JSON | Required fields: id, script, label, description, default_memory, default_cpu, default_runtime, parameters[], preflight{} | Boltz.json: id="Boltz", script="App-Boltz" | app_specs/PredictStructure.json | Yes | Add "tool" enum: boltz/chai/alphafold/esmfold/auto
Parameter types | wsfile (workspace file), folder, string, int, bool, enum, list:wsfile | input_file: wsfile, diffusion_samples: int, output_format: enum["mmcif","pdb"] | app_specs/*.json | Yes | Unified params + tool-specific sections
Preflight function | Returns {cpu, memory, runtime, storage, policy_data{gpu_count, partition, constraint}} | cpu:8, memory:64G, runtime:7200, gpu2 partition, A100¦H100¦H200 | service-scripts/App-*.pl | Yes | Dynamic based on tool + params
Service script structure | AppScript->new(\&run_app, \&preflight); $script->run(\@ARGV) | my $script = Bio::KBase::AppService::AppScript->new() | service-scripts/App-*.pl | Yes | Identical across all apps
Workspace download | $app->workspace->download_file($ws_path, $local_path, 1) | download_workspace_file($app, $input_file, $input_dir) | service-scripts/App-*.pl | Yes | use_shock=1 for files >1KB
Workspace upload | $app->workspace->save_file_to_file($file, {}, $ws_file, $type, 1) | upload_results($app, $output_dir, $output_path) | service-scripts/App-*.pl | Yes | Type detection: structure/json/fasta/binary
Binary discovery | Check PATH → env var (P3_TOOL_PATH) → default /opt/conda/bin | find_boltz_binary() checks PATH, P3_BOLTZ_PATH, /opt/conda/bin | service-scripts/App-*.pl | Yes | Unified: find_tool_binary($tool_name)
Input validation | Detect format by extension then content. FASTA: /^>/m, YAML: /^(version:¦sequences:)/m | detect_input_format($file, $hint) | service-scripts/App-*.pl | Yes | Add auto-routing: YAML→Boltz, FASTA→others
Docker 3-layer pattern | L1: nvidia/cuda → L2: tool+python → L3: BV-BRC runtime+Perl | dxkb/boltz → dxkb/boltz-bvbrc | container/Dockerfile.* | Yes | Per-tool OR delegation pattern
Makefile targets | all, bin, deploy-client, deploy-service, deploy-specs, test-* | make deploy-service copies app_specs + service-scripts to $(TARGET) | Makefile | Yes | Copy from boltzApp/Makefile
CWL stability chain | predict→stabilinnator in CWL Workflow. structure_file output feeds stability input. | protein_stability_pipeline.cwl: boltz.cwl → stabilinnator.cwl | cwl/workflows/ | Phase 3 | Reuse for unified tool CWL
GPU SLURM policy | policy_data: {gpu_count:1, partition:"gpu2", constraint:"A100¦H100¦H200"} | In preflight() return and app_specs preflight{} | Both locations | Yes | ESMFold: GPU optional, skip policy
Environment variables | P3_WORKDIR, P3_DEBUG, P3_LOG_LEVEL, TMPDIR, PERL5LIB, KB_TOP | $ENV{P3_WORKDIR} // $ENV{TMPDIR} // "/tmp" | service-scripts/App-*.pl | Yes | Set P3_LOG_LEVEL default to INFO

## Parameter Map
Unified ↔ Tool Parameter Mapping
Unified CLI Flag | Type | Boltz-2 | Chai-1 | AlphaFold2 | ESMFold (HF) | Notes
<tool> | enum | boltz predict | chai fold | run_alphafold.py | esm-fold-hf | Required positional arg
<input> | file | INPUT_PATH (.yaml) | --fasta | --fasta_paths | -i (.fasta) | FASTA common; Boltz needs YAML
--output-dir, -o | path | --out_dir | output_dir | --output_dir | -o | Required
--num-samples, -n | int | --diffusion_samples (def:1) | --num-diffn-samples (def:5) | --num_multimer_... (def:5) | N/A (deterministic) | Ignored for ESMFold
--num-recycles | int | --recycling_steps (def:3) | --num-trunk-recycles (def:3) | implicit (def:3) | --num-recycles (def:4) | None = use tool default
--sampling-steps | int | --sampling_steps (def:200) | --num-diffn-timesteps (def:200) | N/A | N/A | Only diffusion-based tools
--seed | int | N/A (not exposed) | --seed | --random_seed | N/A (deterministic)
--device | string | --accelerator (gpu/cpu) | --device (cuda:N) | implicit | --cpu-only (flag) | auto = detect GPU
--output-format | enum | --output_format + convert | convert from cif | native pdb | native pdb | Always produce both PDB+CIF
--msa | file/dir | inject into YAML msa: field | --msa-file (after a3m→pqt) | --msa_dir (precomputed) | ignored | A3M is lingua franca
--use-msa-server | flag | --use_msa_server | --use-msa-server | N/A | ignored
--no-msa | flag | omit msa field in YAML | omit msa arg | single-seq A3M | always no-MSA
--boltz-* | pass | Direct pass-through | - | - | - | e.g. --boltz-use-potentials
--chai-* | pass | - | Direct pass-through | - | - | e.g. --chai-constraint-path
--af2-* | pass | - | - | Direct pass-through | - | e.g. --af2-model-preset
--esm-* | pass | - | - | - | Direct pass-through | e.g. --esm-chunk-size